## Sheet1
| Task Details | Status | Task Completion date | Time Line | Remarks
2025-02-11 | Dear TeamKindly revert the acceptance of the device return request by the District (GAUTAM BUDHA NAGAR)Program ID 16393 Student Enrollment number- 20013446 ROHAN VERMA S/O SUBODH KUMAR & BASANTI SRIVASTAVA Token number- 25010171 Mail; sent on- Feb 11, 2025, 4:28 PM | Pending
2025-02-11 | Dear Team PLease Add a column in the report "District-wise Device and Students availability" after the column the "Eligible student for Smartphone ya Tablet" nemed- "Eligible Aadhaar verified students for Smartphone" & "Eligible Aadhaar verified students for Tablet" message sent on group on 11/02/2025 | Pending
2025-02-06 | Issue regarding blocking of Aadhar verified Student. Email sent on- Feb 6, 2025, 12:10 PM | InProgress
2025-02-06 | Dear Team, The option of "left the institution" is not available at Admin logins please check and provide. message sent on group. 04/02/2025 | Waiting for Make it live
2025-02-04 | Dear Team Kinldy fix the issue raised by the district ghaziabad as student is showing department locked but eKYC status is showing as Pending. Button of varification is not available. Screenshots are sent on group on 04/02/2025 | Fixed after block Activity
2025-01-31 | Dear Team Please provide the column/options for session 2024-25 in the sub-dashboard. Also, update it weekly basis. Mail sent on- Jan 31, 2025, 1:07 PM | Making Scheduler for it
2025-01-28 | Dear Team Kindly check the DPC issues raised by the district Sitapur. Message sent on group 28/01/2025 | Pending
2025-01-28 | Dear Team Please provide an analytical report at district login at dashboard. 1) Number of Institutions not uploading the data session wise. - Name of Institution - Name of University - Name of Nodal officer - Phone number of Nodal Officer 2) Number of institution have not been marked delivery (Pilot Phase) - Name of University - Name of Institution - Name of Nodal officer - Pending for Mapping - Pending for Delivery Marking/Photo Upload 3) Number Institution having Pending Adhar Verified students - Name of University - Name of Institution - Name of Nodal officer - Number of students eligiblae for Adhar Verification -Number of students Pending for Adhar verification (excluding the number of delivered) Mail sent on- Jan 28, 2025, 10:02 AM | Pending
2025-01-21 | Dear Team As we received the approval from MD maam for the process of resetting the aadhaar verification status, please find the process that need to be developed for the same :- 1) A new option " Rejection of Adhaar verified Students" should be given under the Transaction Menu of Instituion Login, University login and Department Login. 2) Instituion can see the list of all Adhaar verified students who have not been locked by District for distribution. 3) The Institution can select the students and forward it to University for approval/rejection of request. 4) An alert should be shown to university once it accepts the request as " The Adhaar verification status of Student will be Reset if this request is accepted by Department". 5) If University clicks "ok" then the request will get forwarded to Department and on acceptance of Department the request will show the alert " The aadhar Verification of Student will be Reset if the request is accepted" and data will be rejected completely and adhar verification status will reset. 6) In case the University or Department will Reject the data then The data will stay in "department Locked posititon" Note :- Once the Institution starts the process of Rejection of Aadhar verified students the district should not be allowed to select the data for distribution, until the rejection request is rejected by University or department. Reports will show the results accordingly. Mail sent on- Jan 21, 2025, 4:26 PM | InProgress
2025-01-21 | Please look into the matter (screenshots given below) where the data of students is rejected but then also it is picking up the record on eKYC search page. also this data is uploaded thrice but the search result is picking up the old data not the latest one. Why is it not picking up the latest uploaded data? mail sent on- Jan 21, 2025, 4:22 PM | No issue. All students are same status's why not taking latest record. Their could be possibility that they can forwaord old record.
2025-01-15 | Provide UG/PG course marking option at UBSC while uploading any new course on the portal. | Waiting for making it live.
2025-01-10 | Dear Team Kindly look into the issue raised by the district Devaria as the institution returned the devices and the district accepted the return request of devices but devices are still available to return at the institution login. Institution User ID is- USER ID-DUINST0029 Raise request Token Number 25010165 Mail sent on- Jan 10, 2025, 5:22 PM | Pending
2024-07-27 | Dear Team Kindly look into the issue raised by the district Baharaich as at the option of "Select Students for Distribution Event" the remaining locked column shows as -2. M/s CELKON IMPEX PRIVATE LIMITED(SP)(2023) [Samsung Galaxy A04e (A042F)] The screenshot is attached for your reference Mail sent on- Jul 27, 2024, 4:25 PM | Pending